## 测试报告
Sprint_Daily_Report_07/06
Sprint | 【OBIS-20260622-20260703】
Test ENV | SIT、UAT1、UAT2
Testing Progress | 测试用例整体通过率：73% ¦ Bug 总数：144
Risk/Block | Description | [7 empty] | Need Help
| 1. 测试执行中bug量逐渐增加（38个bug待修复），需开发及时协助修复 | [7 empty] | 开发请及时关注待修复Bug
| 2. 测试中有许多待产品确认的设计和实现点，需产品及时确认和处理 | [7 empty] | 产品请及时响应测试和开发的反馈
Story | Test Design |  |  | Test Execution |  |  |  |  | Story | Ready for Testing
| Design | Review | Review Rate | PASS | FAILED | BLOCKED | Pass Rate | Executable Pass Rate | Status | Yes/No | Ready Date | Comment
Generate File key 修改为tag | 3 | 3 | 100% | 3 | 0 | 0 | 100% | 100% | 待验收 | Yes | 2026-06-30 | 延期
[GPCA] E1-S01：GP CA 对象列表页 | 47 | 47 | 100% | 39 | 1 | 7 | 80% | 97.5% | 测试中 | Yes | 2026-06-29
[GPCA] E1-S02：根 CA 创建 | 28 | 28 | 100% | 17 | 8 | 3 | 60.71% | 68% |  | Yes | 2026-06-26
[GPCA] E1-S03：根 CA 详情页 | 29 | 29 | 100% | 20 | 4 | 5 | 68.97% | 83.33% |  | Yes | 2026-06-26
[GPCA] E1-S04：中间 KA 创建 | 27 | 27 | 100% | 18 | 3 | 6 | 66.67% | 85.71% |  | Yes | 2026-06-26
[GPCA] E1-S05：中间 KA 详情页 | 31 | 31 | 100% | 19 | 3 | 9 | 61.29% | 86.36% |  | Yes | 2026-06-26
[GPCA] E1-S06：OCE 证书创建 | 40 | 40 | 100% | 32 | 5 | 3 | 80% | 86.49% | 测试中 | Yes | 2026-07-01 | 延期
[GPCA] E1-S07：OCE 证书详情页 | 36 | 36 | 100% | 24 | 0 | 12 | 66.67% | 72% | 测试中 | Yes | 2026-07-01 | 延期
[GPCA] E1-S08：SD 证书（Mode B）创建 | 25 | 25 | 100% | 20 | 5 | 0 | 80% | 80% |  | Yes | 2026-07-01 | 延期
[GPCA] E1-S09：SD 证书详情页 | 15 | 15 | 100% | 14 | 1 | 0 | 93.33% | 93.33% |  | Yes | 2026-07-01 | 延期
[GPCA] E1-S10：SD 证书存档管理 | 25 | 25 | 100% | 0 | 0 | 0 | 0% | 0% |  | Yes | 2026-07-01 | 延期
[GPCA] E1-S16：密钥授权（GP-F07） | 10 | 10 | 100% | 0 | 0 | 0 | 0% | 0% |  | Yes | 2026-07-01 | 延期
[GPCA] E1-S17：中间 KA 离线签发 | 19 | 19 | 100% | 14 | 3 | 2 | 73.68% | 82.35% |  | Yes | 2026-06-26
[GPCA] E1-S18：OCE 证书离线签发 | 18 | 18 | 100% | 15 | 2 | 1 | 83.33% | 83% | 测试中 | Yes | 2026-07-01 | 延期
[GPCA] E1-S19：SD 证书（Mode B）离线签发 | 15 | 15 | 100% | 15 | 3 | 0 | 100% | 83.33% |  | Yes | 2026-07-01 | 延期
[PS-Software]S-F01-06: PCSC 读卡器通道类型配置 | 16 | 16 | 100% | 0 | 0 | 0 | 0% | 0% |  | Yes | 2026-07-01 | 延期
[PS-Software]S-F01-07: PCSC 读卡器连接状态展示 | 13 | 13 | 100% | 0 | 0 | 0 | 0% | 0% |  | Yes | 2026-07-01 | 延期
[PS-Software]S-F01-08: 通道类型可用范围配置 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0% |  | Yes | 2026-07-01 | 延期
[PS-Software]S-F03-01: SE Provisioning APDU 中继执行 | 24 | 24 | 100% | 0 | 0 | 0 | 0% | 0% |  | Yes | 2026-07-01 | 延期
[SEMS] E1-S01：SE Profile 列表页 | 24 | 24 | 100% | 22 | 2 | 0 | 91.67% | 91.67% |  | Yes | 2026-06-29
[SEMS] E1-S02：SE Profile 创建与克隆 | 17 | 17 | 100% | 17 | 0 | 0 | 100% | 100% |  | Yes | 2026-06-29
[SEMS] E1-S03a：SE Profile 详情页 — 主框架 | 21 | 21 | 100% | 20 | 1 | 0 | 95.24% | 0% |  | Yes | 2026-06-29
[SEMS] E1-S03b：SE Profile 详情页 — 内容树编辑 | 40 | 40 | 100% | 20 | 0 | 0 | 50% | 100% |  | Yes | 2026-06-29
[SEMS] E1-S04：SE Profile 发布 | 35 | 35 | 100% | 0 | 0 | 0 | 0% | 0% |  | Yes | 2026-06-30 | 延期
[SEMS] E1-S07：Permission Tab（协作者权限管理） | 36 | 36 | 100% | 24 | 5 | 7 | 66.67% | 100% |  | Yes | 2026-07-01 | 延期
[SEMS] E4-S10：边端轻量 TSM 执行规约 | 19 | 19 | 100% | 0 | 0 | 0 | 0% | 0% |  | Yes | 2026-07-01 | 延期
[SEMS] E4-S1：IF-01 SE Profile Definition 输出 | 24 | 24 | 100% | 16 | 0 | 6 | 66.67% | 0% | 测试中 | Yes | 2026-06-30 | 延期
[SEMS] E4-S2：IF-02 SE Profile 列表查询 | 33 | 33 | 100% | 20 | 0 | 10 | 60.61% | 0% | 测试中 | Yes | 2026-06-30 | 延期
[SEMS] E4-S3：IF-03 SD 证书回传（Mode A） | 28 | 28 | 100% | 0 | 0 | 0 | 0% | 0% | 测试中 | Yes | 2026-06-30 | 延期
[SEMS] E4-S9：IF-08 SE Profile 授权数据获取 | 37 | 0 | 0% | 15 | 10 | 7 | 40.54% | 0% | 测试中 | Yes | 2026-06-30 | 延期
product list 页面增加过滤条件 | 10 | 10 | 100% | 10 | 0 | 0 | 100% | 100% | 待验收 | Yes | 2026-06-26
version和batch选择 GF | 10 | 10 | 100% | 10 | 0 | 0 | 100% | 100% | 待验收 | Yes | 2026-06-30
【SE卡片】SE卡片内容说明 | 18 | 18 | 100% | 18 | 0 | 0 | 100% | 100% | 待验收 | Yes | 2026-06-30
【SE卡片】内容导入 | 19 | 19 | 100% | 19 | 0 | 0 | 100% | 100% | 待验收 | Yes | 2026-06-30
【SE卡片】订阅与动作 | 19 | 19 | 100% | 10 | 0 | 0 | 52.63% | 53% | 测试中 | Yes | 2026-06-30
【体验优化P1】Account | 15 | 15 | 100% | 15 | 0 | 0 | 100% | 100% | 待验收 | Yes | 2026-06-26
【体验优化P1】DAC Report | 17 | 17 | 100% | 17 | 0 | 0 | 100% | 100% |  | Yes | 2026-06-26
【体验优化P1】Device History | 14 | 14 | 100% | 14 | 0 | 0 | 100% | 100% |  | Yes | 2026-06-26
【体验优化P1】Factory | 25 | 25 | 100% | 23 | 0 | 2 | 92% | 100% |  | Yes | 2026-06-26
【体验优化P1】Group | 14 | 14 | 100% | 14 | 0 | 0 | 100% | 100% | 待验收 | Yes | 2026-06-26
【体验优化P1】KMS | 17 | 17 | 100% | 17 | 0 | 0 | 100% | 100% |  | Yes | 2026-06-26
【体验优化P1】PKI | 21 | 21 | 100% | 21 | 0 | 0 | 100% | 100% |  | Yes | 2026-06-26
【体验优化P1】Product | 16 | 16 | 100% | 16 | 0 | 0 | 100% | 100% | 待验收 | Yes | 2026-06-26
【体验优化P1】U-safe | 19 | 19 | 100% | 19 | 0 | 0 | 100% | 100% |  | Yes | 2026-06-26
【体验优化P1】全局菜单及导航栏 | 14 | 14 | 100% | 14 | 0 | 0 | 100% | 100% | 待验收 | Yes | 2026-06-26
【体验优化P2】Account详情（不含自注册） | 12 | 12 | 100% | 12 | 0 | 0 | 100% | 100% | 待验收 | Yes | 2026-06-30
【体验优化P2】Factory详情 | 51 | 51 | 100% | 51 | 0 | 0 | 100% | 100% |  | Yes | 2026-06-29
【体验优化P2】Group详情 | 15 | 15 | 100% | 15 | 0 | 0 | 100% | 100% | 待验收 | Yes | 2026-06-26
【卡片编辑】assests 卡片自定义 | 26 | 26 | 100% | 26 | 0 | 0 | 100% | 100% |  | Yes | 2026-06-30
【卡片编辑】overview展示内容改动 | 44 | 44 | 100% | 44 | 0 | 0 | 100% | 100% | 待验收 | Yes | 2026-06-30
【卡片编辑】自定义卡片 | 24 | 24 | 100% | 24 | 0 | 0 | 100% | 100% | 待验收 | Yes | 2026-06-30
【卡片编辑】选择module类型 | 30 | 30 | 100% | 30 | 0 | 0 | 100% | 100% | 待验收 | Yes | 2026-06-30
【自注册】003-01: 欢迎弹窗与侧边栏引导 | 15 | 15 | 100% | 15 | 0 | 0 | 100% | 100% | 测试中 | Yes | 2026-06-30
【自注册】003-02: 场景引导与完成追踪 | 35 | 35 | 100% | 35 | 0 | 0 | 100% | 100% | 待验收 | Yes | 2026-06-26
【自注册】003-03: 常驻工具栏与资源中心 | 13 | 13 | 100% | 10 | 0 | 3 | 76.92% | 100% | 待验收 | Yes | 2026-06-26
【自注册】003-04: Welcome内容管理 | 17 | 17 | 100% | 15 | 0 | 2 | 88.24% | 100% | 待验收 | Yes | 2026-06-26
【自注册】004-05: 统一联系销售弹窗与Lead落库 | 16 | 16 | 100% | 16 | 0 | 0 | 100% | 100% | 待验收 | Yes | 2026-06-26
【自注册】权限配置Phase1 | 12 | 12 | 100% | 12 | 0 | 0 | 100% | 100% | 待验收 | Yes | 2026-07-01 | 延期
移除 Attachment File 分类 | 6 | 6 | 100% | 6 | 0 | 0 | 100% | 100% | 待验收 | Yes | 2026-06-30 | 延期
总计 | 1299 | 1262 | / | 952 | 56 | 85 | 73.29% | 94.12% | / | / | /
Bug Total | Status/Statistics
| To Do | Testing | Fixing | Confirming | Clarifying | Done | closed | Total | Fixed Rate
P0 | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 4 | 75%
P1 | 1 | 4 | 0 | 0 | 3 | 2 | 3 | 13 | 38%
P2 | 20 | 10 | 3 | 0 | 1 | 55 | 6 | 95 | 64.21%
P3 | 12 | 6 | 1 | 0 | 1 | 11 | 1 | 32 | 38%
Total | 34 | 20 | 4 | 0 | 5 | 69 | 12 | 144 | 56.25%
Bug Reopen | Link/Details
| Priority | Status | Link |  |  |  | Summary |  |  |  |  | Reopen Times
1 | P2 | To Do | https://project.feishu.cn/obis/bug/detail/7035307368 |  |  |  | 【GPCA】导入证书时，“Import” 按钮需点击 2 次才可导入证书 |  |  |  |  | 1
2 | P2 | Testing | https://project.feishu.cn/obis/bug/detail/7034234347 |  |  |  | 【GPCA-根CA】创建根CA，Certificates Identifier 填写系统已有的证书Certificates Identifier ，可保存成功 |  |  |  |  | 2
3 | P2 | Testing | https://project.feishu.cn/obis/bug/detail/7034234347 |  |  |  | 【GPCA-根CA】创建根CA，Certificates Identifier 填写系统已有的证书Certificates Identifier ，可保存成功 |  |  |  |  | 2
4 | P2 | Fixing | https://project.feishu.cn/obis/bug/detail/7035464800 |  |  |  | 【GPCA-根CA】GPCA 证书详情布局和UI不一致 |  |  |  |  | 2
5 | P2 | Fixing | https://project.feishu.cn/obis/bug/detail/7035492400 |  |  |  | 【GPCA-根CA】GPCA 创建证书页面，证书序列号非1-16字节Hex字符串，提示文案有误 |  |  |  |  | 1
Bug List（P0/P1） | Link/Details
| Priority | Status | Link |  |  |  | Summary
1 | P0 | To Do | https://project.feishu.cn/obis/bug/detail/7040729555 |  |  |  | 【GPCA】SD 证书无法签发
2 | P0 | To Do | https://project.feishu.cn/obis/bug/detail/7040493770 |  |  |  | 【iot-SEMS】SE Profile相关批次创建失败
3 | P1 | Clarifying | https://project.feishu.cn/obis/bug/detail/7034306672 |  |  |  | 【Iot-OBIS】Welcome Page - 欢迎页面的教程视频需要替换成真实的视频
4 | P1 | Clarifying | https://project.feishu.cn/obis/bug/detail/7035201092 |  |  |  | 【IOT-Product】Overview界面无Add Module 按钮（UI design 不一致）
5 | P1 | Testing | https://project.feishu.cn/obis/bug/detail/7035323354 |  |  |  | 【GPCA-根CA】根证书有效期到期后，证书状态未更新为过期
6 | P1 | Testing | https://project.feishu.cn/obis/bug/detail/7035543886 |  |  |  | 【GPCA】在 External CA-KLCC 下尝试导入 SD 证书，实际被导入的证书为 KA，导入成功
7 | P1 | Clarifying | https://project.feishu.cn/obis/bug/detail/7036166618 |  |  |  | 【IOT-Product】卡片编辑部分国际化未配置
8 | P1 | Testing | https://project.feishu.cn/obis/bug/detail/7040526235 |  |  |  | 【SE卡片-Version创建】Version创建时未校验module下有Inactive状态的SE资产
9 | P1 | Testing | https://project.feishu.cn/obis/bug/detail/7040544797 |  |  |  | 【GPCA-根CA】创建根证书，选择外部导入，输入证书数据和name后点击Import，提示"internal server error"
10 | P1 | To Do | https://project.feishu.cn/obis/bug/detail/7040696494 |  |  |  | 【GPCA】在 External CA-KLCC 下尝试导入 KA 证书，实际被导入的证书为 SD，导入成功